## Backlog
Backlog for OHC Medicine Portal
Sr. No. | Task Name | Task Description | Status | Assigned to | Start Date | End Date | Duration | % Complete | Remarks
Master Table Creation in DB
1 | User Master | (UserID, User Name, EmailID, Employee Code, Department Name, isActive,Password) | Pending
2 | Department Master | (DeptID, Department Name, Isactive) | Pending
3 | Medicine Master | (MedicineID, Medicine Name, Type, isactive) | Pending
4 | Vendor Master | VendorID, Vendor Name, Address, Licence No., isactive | Pending
5 | Employee Cum Patient Master | Employee ID, Employee Name, Emp Code, DOB, Address, EMP type, Isactive, | Pending
6 | First Aid Location Master | LocationID, LocationName, Department Name, Isactive | Pending
7 | First Aid Volunteer Master | VolunteerID, VolunteerName, EMPCode, Department, Address, Isactive | Pending
Pending
Execution Forms
8 | User Login | Login page to be created so that user can login in application with their credntials. | Pending
9 | Admin Dashboard Design | Dashbaord will be designed and all options and data will showing here. | Pending
10 | User Dashboard Design | Dashbaord will be designed and user options will show only. | Pending
11 | Medicine Receiving Form | Medicine Name, Qty, Batch Number, Expiry, Type, Vendor Name | Pending
12 | Inventory Tabular view | Medicine Inventory shows in tabular data | Pending
13 | Medicine Issuance to other unit/first add | Issue to dept name, Issue Date, Medicine name, Qty, Batch No., | Pending
14 | Medicine prescribe to employee cum patient | Employee Name, Problem, Medicine, Qty, Batch No. | Pending
15 | Inspection form of Emegency kit, Ambulance and First Add | Ispection list as per EHS dept provided | Pending
Reports
16 | Monthly Inventory Report | As per the format given by EHS Dept. | Pending
17 | Medicine Procurement Report | As per the format as per request slip | Pending
18 | Inspection Report | As per the format | Pending
19 | Medicine Issuance Report | As per the inspection format | Pending
20 | Item Wise Consumption Report | As per the format | Pending
21 | First Add Report with their location | As per the format | Pending

## Dimpal
SN. | Task | Target Date | Status
Sprint 1 | Create DB and setup Application | 2023-05-10 | Done
| User Login | 2023-05-10 | Done
| Dashboard | 2023-05-10 | Done
| User Master | 2023-05-11 | Done
| Department Master | 2023-05-11 | Done
| Medicine Master | 2023-05-11 | Done
| Vendor Master | 2023-05-12
| Employee Cum Patient Master | 2023-05-12
| First Aid Location Master | 2023-05-12
| First Aid Volunteer Master | 2023-05-12
Sprint 2 | Medicine Receiving Form | 2023-05-15
| Inventory Tabular view | 2023-05-15
| Medicine Issuance to other unit/first add | 2023-05-16
| Medicine prescribe to employee cum patient | 2023-05-17
| Inspection form of Emegency kit, Ambulance and First Add | 2023-05-19
Sprint 3 | Monthly Inventory Report | 2023-05-22
| Medicine Procurement Report | 2023-05-23
| Inspection Report | 2023-05-24
| Medicine Issuance Report | 2023-05-25
| Item Wise Consumption Report | 2023-05-26
| First Add Report with their location | 2023-05-29
| Testing | 2023-05-01
| Review | 2023-05-02

## Project Plan New
Medicine Portal Development Plan(Agile Methodology)
Sr. No. | Task | Sprint | Status | Assigned to | Start Date | End Date | Duration | % Complete | Dependencies | Remarks
SPRINT 1 - User Login Module
1 | User Master | SPRINT 1 | Pending
2 | Department Master | SPRINT 1 | Pending
3 | Dashboard Creation | SPRINT 1 | Pending
4 | Testing of pages | SPRINT 1 | Pending
5 | Review Meeting with Stakeholder | SPRINT 1 | Pending
SPRINT 2 - Master Creation
6 | Medicine Master | SPRINT 2 | Pending
7 | Vendor Master | SPRINT 2 | Pending
8 | Medicine Request Form | SPRINT 2 | Pending
9 | Testing of pages | SPRINT 2 | Pending
SPRINT 3 - Medicine Recieving
10 | Medicine Receiving Form | SPRINT 3 | Pending
11 | Medicine Inventory Report | SPRINT 3 | Pending
12 | Testing of pages | SPRINT 3 | Pending
13 | Review Meeting with Stakeholder | SPRINT 3 | Pending
SPRINT 4 - Medicine Issuance
14 | Department Master | SPRINT 4 | Pending
15 | Employee Cum Patient Master | SPRINT 4 | Pending
16 | First Add Location Master | SPRINT 4 | Pending
17 | Doctor Prescription Form | SPRINT 4 | Pending
SPRINT 5 - Inspection
20 | Medicine Issuance Form to Others | SPRINT 5 | Pending
21 | Inspection of Emergency Kit | SPRINT 5 | Pending
22 | Inspection of Fisrt Add | SPRINT 5 | Pending
23 | Inspection of Ambulance | SPRINT 5 | Pending
24 | Testing of pages | SPRINT 5 | Pending
25 | Review Meeting with Stakeholder | SPRINT 5 | Pending
SPRINT 6 - Reports
26 | Inventory Report | SPRINT 6 | Pending
27 | Medicine Issuance Report | SPRINT 6 | Pending
28 | Testing of pages | SPRINT 6 | Pending
29 | Review Meeting with Stakeholder | SPRINT 6 | Pending
SPRINT 7 - Final Review
30 | Inspection Report | SPRINT 7 | Pending
31 | Consumption Report | SPRINT 7 | Pending
32 | Final Review of Application and Club | SPRINT 7 | Pending
32 | Testing of Application | SPRINT 7 | Pending
33 | Review Meeting with Stakeholder | SPRINT 7 | Pending